## WBS
ID | Task | Phase | Priority | Assignee | Depends On | Effort(d) | FR Ref | GitHub | Branch | Milestone | Status
T-001 | Repo, CI/CD, branch strategy, doc structure | 0-Env | P0 | PM-Lisa | - | 2 | NFR-007 | #101 | feature/101-repo-setup | M1 | Backlog
T-002 | Dev/Staging/Prod environments (Nginx/Redis) | 0-Env | P0 | BE-Tran | T-001 | 3 | NFR-002 | #102 | feature/102-environments | M1 | Backlog
T-003 | Shopify app + Customer/Order API + Webhook | 0-Env | P0 | BE-Kim | T-002 | 3 | FR-007,010,043 | #103 | feature/103-shopify-integ | M1 | Backlog
T-004 | Fulfillment webhook + status mapping | 0-Env | P0 | BE-Kim | T-003 | 2 | FR-043,NFR-010 | #104 | feature/104-fulfillment | M1 | Backlog
T-005 | Klaviyo integration (campaigns/segments) | 0-Env | P1 | BE-Tran | T-002 | 3 | FR-041 | #105 | feature/105-klaviyo | M1 | Backlog
T-006 | Odoo JSON-RPC connector (products/inventory) | 0-Env | P1 | BE-Tran | T-002 | 3 | FR-042 | #106 | feature/106-odoo | M1 | Backlog
T-007 | Google Drive KB sync connector | 0-Env | P0 | BE-Kim | T-002 | 2 | FR-021 | #107 | feature/107-gdrive-sync | M1 | Backlog
T-008 | MySQL schema + ERD | 1-Backend | P0 | BE-Kim | T-002 | 4 | NFR-007 | #108 | feature/108-db-schema | M1 | Backlog
T-009 | Chat Orchestrator skeleton (Next.js, RabbitMQ) | 1-Backend | P0 | BE-Kim | T-008 | 4 | FR-001 | #109 | feature/109-orchestrator | M1 | Backlog
T-010 | Session lifecycle + i18n resolver | 1-Backend | P0 | BE-Tran | T-009 | 3 | FR-001,002,NFR-003 | #110 | feature/110-session-i18n | M1 | Backlog
T-011 | Auth Gate (Shopify/social/guest lookup) | 1-Backend | P0 | BE-Kim | T-003,T-010 | 5 | FR-006~009 | #111 | feature/111-auth-gate | M1 | Backlog
T-012 | RAG service + Knowledge Store + GDrive | 1-Backend | P0 | BE-Tran | T-007,T-009 | 6 | FR-013,020,021,022 | #112 | feature/112-rag | M1 | Backlog
T-013 | Conversation Log Store + CJM emitter | 1-Backend | P0 | BE-Kim | T-008 | 3 | FR-018,026,NFR-007 | #113 | feature/113-log-cjm | M1 | Backlog
T-014 | Notification Center container (tabs/badges/settings) | 2-Widget | P0 | FE-Lee | T-010 | 4 | FR-028 | #114 | feature/114-notif-center | M2 | Backlog
T-015 | Welcome + scenario menu + AI disclosure | 2-Widget | P0 | FE-Lee | T-014 | 3 | FR-002,003,038,NFR-009 | #115 | feature/115-welcome-menu | M2 | Backlog
T-016 | Notification inbox + filters + read state | 2-Widget | P0 | FE-Vu | T-014 | 4 | FR-029,NFR-011 | #116 | feature/116-notif-inbox | M2 | Backlog
T-017 | Orders panel + detail + delivery stepper | 2-Widget | P0 | FE-Vu | T-011,T-016 | 5 | FR-030,031,032,033 | #117 | feature/117-orders-panel | M2 | Backlog
T-018 | Chat UI + Product Help submenu + RAG render | 2-Widget | P0 | FE-Lee | T-012,T-015 | 5 | FR-005,013,038 | #118 | feature/118-chat-ui | M2 | Backlog
T-019 | Order status / cancel-refund flow | 2-Widget | P0 | FE-Vu | T-011,T-017 | 3 | FR-010,011,012 | #119 | feature/119-order-flow | M2 | Backlog
T-020 | User notification preference center | 2-Widget | P0 | FE-Vu | T-014 | 2 | FR-049 | #120 | feature/120-notif-prefs | M2 | Backlog
T-021 | Logged-in personalization header | 2-Widget | P1 | FE-Lee | T-010 | 2 | FR-050 | #121 | feature/121-personalize | M2 | Backlog
T-022 | Notifier + channel mapping (in-app/email/SMS/WebPush) | 3-Notif | P0 | BE-Tran | T-013 | 5 | FR-023,024,NFR-005 | #122 | feature/122-notifier | M2 | Backlog
T-023 | Order/fulfillment webhook -> notification | 3-Notif | P0 | BE-Kim | T-004,T-022 | 3 | FR-043 | #123 | feature/123-order-notif | M2 | Backlog
T-024 | Review request (N-day) + writing | 3-Notif | P1 | FE-Lee | T-017,T-022 | 4 | FR-034 | #124 | feature/124-reviews | M3 | Backlog
T-025 | Affiliate program flow | 3-Notif | P1 | FE-Vu | T-015,T-013 | 4 | FR-035 | #125 | feature/125-affiliate | M3 | Backlog
T-026 | Restock alert + subscription mgmt | 3-Notif | P1 | BE-Tran | T-006,T-022 | 4 | FR-036,037 | #126 | feature/126-restock-sub | M3 | Backlog
T-027 | Multi-channel contact support card | 3-Notif | P0 | FE-Lee | T-015 | 2 | FR-039 | #127 | feature/127-contact | M3 | Backlog
T-028 | Event/coupon campaign + Klaviyo targeting | 3-Notif | P1 | BE-Tran | T-005,T-022 | 4 | FR-040,041 | #128 | feature/128-campaign | M3 | Backlog
T-029 | Live agent console + handoff | 4-Admin | P0 | FE-Lee | T-012,T-013 | 6 | FR-015,016,017 | #129 | feature/129-agent-console | M2 | Backlog
T-030 | AI agent-assist briefing | 4-Admin | P1 | BE-Tran | T-029 | 5 | FR-045 | #130 | feature/130-ai-assist | M3 | Backlog
T-031 | Admin monitoring dashboard + analytics | 4-Admin | P0 | FE-Vu | T-013,T-022 | 5 | FR-044 | #131 | feature/131-admin-dash | M3 | Backlog
T-032 | Conversation history (search/view/export) | 4-Admin | P0 | FE-Vu | T-013 | 3 | FR-046,019 | #132 | feature/132-conv-history | M3 | Backlog
T-033 | AI Setting/Chat Setting (bot/rules/knowledge/scenario) | 4-Admin | P0 | FE-Lee | T-012 | 5 | FR-047,022,003 | #133 | feature/133-ai-setting | M3 | Backlog
T-034 | Customer & Product management modules | 4-Admin | P1 | FE-Vu | T-006,T-003 | 4 | FR-048 | #134 | feature/134-cust-prod-mgmt | M3 | Backlog
T-035 | Admin notification dispatch / Event Setting / Recipes | 4-Admin | P0 | FE-Lee | T-022,T-028 | 4 | FR-025,040 | #135 | feature/135-admin-notif | M3 | Backlog
T-036 | CCPA compliance (consent/opt-out/deletion/retention) | 5-QA | P0 | BE-Kim | T-013 | 4 | NFR-004 | #136 | feature/136-ccpa | M2 | Backlog
T-037 | i18n content EN/ES/KO | 5-QA | P0 | FE-Lee | T-010 | 3 | NFR-003 | #137 | feature/137-i18n-content | M2 | Backlog
T-038 | Unit tests (TC-001~) | 5-QA | P0 | QA-Park | T-019,T-023 | 5 | all P0 | #138 | feature/138-unit-tests | M4 | Backlog
T-039 | Integration / E2E tests (S1~S17) | 5-QA | P0 | QA-Park | T-038 | 6 | all | #139 | feature/139-e2e-tests | M4 | Backlog
T-040 | Performance & hardening | 5-QA | P0 | BE-Tran | T-012,T-014 | 4 | NFR-001,002,011 | #140 | feature/140-performance | M4 | Backlog

## Milestones
Milestone | Completion Criteria | Tasks | Target
M1 Foundation | Environments, integrations, DB/ERD, orchestrator, auth, RAG, logging | T-001~T-013 | Week 4
M2 MVP Widget | Notif Center, chat/RAG, auth, orders/tracking, order flow, prefs, notifier, order notif, agent console, CCPA, i18n | T-014~T-023,T-029,T-036,T-037 | Week 8
M3 Full Features | Reviews, affiliate, restock/subscription, campaign, AI-assist, admin dashboard/history/settings, cust/prod mgmt | T-024~T-028,T-030~T-035 | Week 12
M4 QA & Release | Unit+E2E+performance passed; critical/major bugs=0 | T-038~T-040 | Week 14

## Effort
Phase | Tasks | Effort (man-days)
Phase 0 - Environment & Integrations | T-001~T-007 | 18
Phase 1 - Backend Foundation | T-008~T-013 | 25
Phase 2 - Customer Widget | T-014~T-021 | 28
Phase 3 - Notifications & Flows | T-022~T-028 | 26
Phase 4 - Escalation & Admin | T-029~T-035 | 32
Phase 5 - Cross-cutting & QA | T-036~T-040 | 22
TOTAL (40 tasks) |  | 151